## Sheet1
Year | 2020 | 2021 | [12 empty] | 2021
Month | December | Januar | February | March | April | May | June | July | August |  | September | October | November | December | Januar | February | March | April | May | June | July | August | September | October | November | December
FCR | Revise and submit article
Supplemental study | Set up | Sample collection |  | Data processing |  | Article |  | Revise and submit
Study 1a | Sequence samples | Data processing |  | Article |  | Revise and submit
Study 1b | [5 empty] | Sequence samples | Data processing |  | Article |  | September: Revise and submit
Thesis | Write outline | Background |  | Background |  | Defence
Deadlines |  | Submit FCR article |  |  |  | Submit 1st draft cfDNA | Submit cfDNA |  |  | Write thesis | bar: September to December
| Submit 1st draft FCR article | Finish thesis outline |  | Finish thesis background | Submit 1st draft CMT | Submit CMT article |  |  |  |  | October: Appoint Comittee; December: Submit thesis
Planning
| Writing |  |  |  | FCR stuff | Preanalytical concerns cfDNA | Canine mammary tumors | Thesis
| Data |  |  |  | Submit to MLA | Buy necessities | Sequence samples | Outline
| Revise |  |  |  | Revise | Find Tape Station | Process data | Background
| Sample collection |  |  |  | Submit to journal | Students? | Analyze data | Materials and methods
[5 empty] | Revise | Do experiments | Write article | Defence
[5 empty] | Publish | Analyse data | Submit to MLA
[6 empty] | Write article | Revise
[6 empty] | Submit to MLA | Submit to journal
[6 empty] | Revise | Revise
[6 empty] | Submit to journal | Publish
Revise
Publish

## Sheet2
Year | 2020 | 2021 | [11 empty] | 2022
Month | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Study 1a | 2020 Dec: Data processing; 2021 Dec: Article; 2022 Feb: Revise and submit
Study 1b | 2020 Dec: Sample collection; 2021 Nov: Data processing; 2021 Dec: Article; 2022 Feb: Revise and submit
Supplemental study | 2020 Dec: Set up; 2021 Jan: Sample collection; 2021 Apr: Data processing; 2021 Jul: Write article; 2021 Aug: Revise and submit
Study 2 | 2020 Dec: Revise and submit article
Thesis: Write Deadlines
| Outline | Background |  | Materials and methods |  | Results |  | Discussion | Intro | Write thesis
[11 empty] | Appoint Comittee |  | Submit thesis